## Sheet1
Website Services Inc.
|  |  |  | PROJECTS |  |  | DELIVERABLE(S)
AT RISK | STATUS | PRIORITY | DEADLINE | TASK | DESCRIPTION | ASSIGNED TO | DELIVERABLE | % DONE | FIXED COST
No | Complete | High | 3 weeks | Requirements Analysis | Gather and analyze requirements for the e-commerce website, including server hardware, operating system, and catalogue data upload functionality. | Business Analyst |  | 100% | 40690
Yes | Complete | Medium | 1 weeks | Design | Collaborate with the design team to create mock-ups and wireframes for the website, ensuring they align with the client's requirements. | Desigher & Business Analyst |  | 100% | 18100
No | Complete | High | 2 week | Building/Development | Develop the website based on the approved design, including server setup, catalogue data upload, and integration of the billing plug-in. | Developer |  | 100% | 36700
No | Complete | Medium | 1 week | Testing | Define and execute test cases to ensure the website meets the specified requirements and quality standards. | Test Analyst & Business Analyst |  | 100% | 22775
Yes | Complete | High | 1 week | Hardware installation | Installation of the necessary hardware equipment. | Technician |  |  | 9010
Yes | Complete | Medium |  | Server H/W and OS | Setting up the required Server Hardware and Operating System. | Business Analyst |  |  | 59800
Yes | Complete | High | 2 days | Installation onto server | Installation onto server | Technician |  |  | 5490
No | In Progress | Low | 4 week | Cataloque data and image upload | Cataloque data and image upload | Developer |  | 100% | 14300
No | Complete | Low | 2 days | Training and Handover | Provide training to the client on how to use and maintain the website, including documentation and support materials. | Business Analyst |  | 100% | 10988
No | Not Started | Medium | 4 weeks | Post-implementation Support | Provide ongoing support to the client, addressing any issues that arise and ensuring the website continues to meet their needs. | Business Analyst |  | 0% | 33385
No | Overdue | High | 1 day | Payment Terms | 50% upfront, 25% on installation, and 25% after the support phase is complete. | Business Analyst & Client (Stakeholders) |  | 100%
No | In Progress | High | 2 days | Quality Assurance | Quality Assurance: Ensure the website is quality assured to run on Chrome, Explorer, Firefox, and Mozilla. | Test Analyst & Business Analyst |  | 50%
No | On Hold | High | 1 day | Client Responsibilities | Provide DSL and server space before installation. | Business Analyst & Client (Stakeholders) |  | 10%
[8 empty] | Total in Rands | 251 238